## Slide 1
Portfolio Summary
Q4 2025 Update

## Slide 2
Portfolio Overview
12
Active Sites
4.2 GW
Total Capacity
6
States
$1.2B
Total Investment

## Slide 3
Site Status Summary
Site | State | MW | Stage | Target Date
Rogers County | OK | 500 | Development | Q2 2028
Mayes Industrial | OK | 750 | Due Diligence | Q4 2028
Pinal Solar | AZ | 400 | Construction | Q1 2026
Navajo Gateway | NM | 600 | Permitting | Q3 2027
West Texas Hub | TX | 1,000 | Development | Q1 2029

## Slide 4
Q4 Priorities
• Close Rogers County PSA by December 15
• Complete Mayes Industrial site assessment
• Submit Pinal Solar construction permits
• Finalize transformer procurement for 3 sites
• Begin Navajo Gateway environmental review

## Slide 5
Key Risks & Mitigations
• Supply Chain: Transformer lead times extending - secured slots with 2 manufacturers
• Regulatory: ERCOT interconnection delays - pursuing fast-track options
• Market: Power prices volatile - hedging strategies in place
• Execution: Resource constraints - adding 2 project managers