## Slide 1
Rogers County Site Profile
Oklahoma - 500 MW Opportunity

## Slide 2
Site Overview
• Location: Rogers County, Oklahoma
• Target Capacity: 500 MW
• Land Status: PSA in negotiation
• Interconnection: Queue position #247 at Tulsa North 345kV
• Water: Municipal water available within 2 miles
• Fiber: Multiple carriers present along Highway 66

## Slide 3
Key Metrics
500
Target MW
2028
Energization
$45M
Land Cost
320
Acres

## Slide 4
Timeline Milestones
Milestone | Target Date | Status
Site Control | Q2 2025 | In Progress
SIS Complete | Q3 2025 | Pending
Facilities Study | Q1 2026 | Scheduled
IA Execution | Q3 2026 | Future
Energization | Q2 2028 | Future

## Slide 5
Risk Factors
• Queue congestion - PSO processing delays reported
• Transformer lead time extending to 4+ years
• County zoning requires special use permit
• Competing projects in area may impact capacity allocation